# Terms of Reference

Feasibility Study: Community Shop for Helmdon Parish Council

# 1. Introduction

Helmdon Parish Council seeks to explore the viability of establishing a community shop within the rural village of Helmdon, which has approximately 1,000 inhabitants, a primary school, a preschool, and a pub. This terms of reference document outlines the purpose, objectives, scope, methodology, and governance for a feasibility study into the proposed community shop.

# 2. Purpose

The purpose of this study is to assess whether opening a community shop in Helmdon is a viable and sustainable option that would meet the needs of local residents and complement existing village amenities.

# 3. Objectives

- To determine the demand for a community shop among Helmdon residents and stakeholders.

- To assess the financial viability and sustainability of the project, including funding options and operational models.

- To consider the potential social, economic, and environmental benefits or impacts of a community shop.

- To evaluate potential locations and premises within the village for the shop.

- To identify potential challenges, risks, and mitigation measures.

- To provide clear recommendations for the Parish Council on whether to proceed with the project.

# 4. Scope

- Engagement with local residents, businesses (including the pub), school, preschool, and other stakeholders

- Analysis of community needs and preferences regarding goods, services, and opening hours.

- Review of successful community shop models in similar rural settings.

- Estimation of start-up and running costs, income projections, and funding/grant opportunities.

- Assessment of possible sites, including ownership, access, planning permissions, and suitability.

- Consideration of staffing models (paid, volunteer, hybrid).

- Exclusion: The study will not include the management of the shop post-opening or decisions on specific suppliers.

# 5. Methodology

A project plan will be developed, which will include:

- Desktop research on community shops in comparable villages.

- Surveys and/or public meetings to gauge local interest and needs (building on the data from the 2024 Parish Plan Village Survey).

- Consultation with local organisations (school, preschool, pub, community groups).

- Site visits and assessments of potential premises.

- Financial modelling and risk analysis.

- Review of legal, regulatory, and insurance requirements.

# 6. Membership, Governance and Reporting

- The Community Shop Working Group will consist of at least 2 appointed Parish Councillors and also volunteer Helmdon residents. The group may co-opt additional members with Relevant expertise as required.

- A summary of progress will be provided to each Parish Council meeting.

- A draft report with findings and recommendations will be presented to the Parish Plan Working Group prior to presenting the final report to the Parish Council for consideration and decision.

# 7. Timescales

- Project initiation: January 2026

- Community engagement and research: January – May 2026

- Analysis and draft reporting: July 2026

- Final report to Parish Council: Sept 2026